## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
Example : All tasks were completed on time. Team communication was seamless. | Requirements changed mid-sprint. | Plan for a buffer to handle scope changes. | Set stricter deadlines for finalizing requirements. | Example
Identified suitable public datasets and validated feasibility of the research framework | Initial difficulty in aligning heterogeneous datasets | Create a standardized feature mapping strategy across datasets | Define common feature schema before preprocessing
Successfully implemented data preprocessing pipeline including imputation and encoding | Time constraints due to academic and placement commitments | Improve time allocation with weekly milestones | Prepare a sprint-wise implementation plan
Ensemble learning model implemented and validated | Learning curve associated with SHAP explainability | Allocate dedicated time for explainability research | Refer additional SHAP documentation and examples
Generated instance-level SHAP explanations for predictions | Limited lifestyle features in some datasets | Combine clinical indicators with proxy lifestyle features | Document feature limitations clearly in research paper
Maintained proper Agile documentation in MS Planner and OneNote | Parallel documentation and coding was challenging | Update documentation incrementally | Allocate fixed time slots for documentation