## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
Ensemble Stability: The Soft-Voting Ensemble provided much more stable probabilities than any single model. | GitHub File Limits: The 200MB model file was blocked by GitHub's 100MB upload limit. | Implement Git LFS: Use Large File Storage to handle high-volume binary files. | Installed Git LFS and tracked .pkl files using pointer logic.
Explainable AI Integration: SHAP TreeExplainer provided clear clinical reasoning for the Diabetes module. | Preprocessing Latency: Initial local testing showed slow inference due to heavy SHAP calculations. | Optimize XAI Backend: Limit SHAP calculation to the top 10 most impactful features. | Reduced feature attribution depth to optimize API response time.
Frontend/Backend Sync: The Pydantic schema perfectly matched the Next.js form state. | Version Mismatch: Some library version conflicts between Google Colab and local environment. | Standardize Requirements: Create a strict requirements.txt for the local environment. | Froze dependencies in requirements.txt to match Colab versions.
Clinical Reasoning: The model successfully prioritized high-impact features like BMI and HighBP. | Data Labeling: Minor confusion initially on mapping survey response IDs to human-readable text. | Create Mapping Dictionary: Build a JSON mapper for frontend display. | Developed a feature-to-label mapper for the Risk Diagnostics view.
Local Inference Speed: The backend response time for basic predictions was optimized successfully. | SHAP Computation Cost: Generating the full SHAP explanation for the ensemble added significant latency. | Background Computing: Compute SHAP values on a separate thread or cache results for common profiles. | Optimized the FastAPI endpoint to compute SHAP only for relevant features.
Ensemble Logic Defense: The reasoning for "Soft Voting" was well-documented for the panel presentation. | Cross-Platform Scaling: The StandardScaler produced different results if not loaded correctly in the backend. | Pipeline Export: Export the entire Scikit-learn Pipeline (Scaler + Model) as a single object. | Re-exported the pipeline to ensure scaling and prediction are always synchronized.
UI Aesthetics: The Material 3 design system made the "Risk Diagnostics" page look professional. | Graph Readability: The initial Recharts bar chart for SHAP values was cluttered with too many features. | Top-K Visualization: Only show the top 5 contributing features in the main UI view. | Filtered the SHAP data array to show the top 5 "Impact Drivers" only.
Code Modularity: The frontend was successfully decoupled from the backend logic. | Documentation Lag: Keeping the Functional Document updated with rapid ML changes was difficult. | Automated Test Logs: Use a logging system to automatically capture test results during development. | Set up a small logging script to track model accuracy during iterative training runs.